## 2025-2026
SCI- $2,542,227 - SRA - $2,084,976 Capital Funding Memo : B08 2024 |  |  | 2025-2026 CAPITAL WORKS
School | Description | Est Budget |  | Phase | Funding Source | Project Status
SITE WORKS
Blessed Sacrament | Septic System | 500000 |  | Planning | School Condition Improvement
St.Patrick (Brantford) | Paving | 300000 |  | Planning | School Renewal Allocation
St.Leo | Paving | 300000 |  | Planning | School Renewal Allocation
Assumption | Resurface running track | 250000 |  | Planning | School Renewal Allocation
Subtotal: |  | 1350000
Funding Allocation:
Unallocated/ Contingency:
Building
Holy Trinty | Pahse 1 roofing | 800000 |  | Planning | School Renewal Allocation
Subtotal: |  | 800000
Funding Allocation:
Unallocated/ Contingency:
Mechanical HVAC
St.Patrck (Haldimand) | HVAC Phase 1 Classrooms | 1000000 |  | Planning | School Condition Improvement
St.Theresa | HVAC Gym Unit | 350000 |  | Planning | School Condition Improvement
St.Mary Haldimand | HVAC Gym unit | 300000 |  | Planning | School Condition Improvement
St.Francis Cabrini | HVAC Gym Unit |  | 600000 | Planning | School Condition Improvement
Subtotal: |  | 2250000
Funding Allocation:
Unallocated/ Contingency:
SERVICES
Subtotal: |  | 0
Funding Allocation:
Unallocated/ Contingency:
,
,

## 2024-2025
SCI- $2,529,450 - SRA - $1,999,281 Capital Funding Memo : B08 2024 |  |  | 2024-2025 CAPITAL WORKS
School | Description | Est Budget |  | Phase/Tender Issue | Funding Source | Project Status
SITE WORKS
Assumption College | Parking lot improvments Student Parking | 200000 |  | Complete | School Renewal Allocation
St.Bernards | Playground paving improvments | 100000 |  | Complete | School Renewal Allocation
Assumption College | Running Track | 400000 |  | Complete | Board Funded
Blessed Sacrament | Septic/Sanitary System replacment | 500000 |  | Planning | School Condition Improvement | Postponed to 20205/2026 MECP permit
Subtotal: |  | 1200000
Funding Allocation:
Unallocated/ Contingency:
Building
St..Patrick Brantford | All Windows and Building envelope upgrades | 300000 |  | Complete | School Renewal Allocation
St.Patrick Haldimand | All Interior Doors | 200000 |  | Complete | School Renewal Allocation
Subtotal: |  | 500000
Funding Allocation:
Unallocated/ Contingency:
Mechanical HVAC
Holy Trinity | HVAC Chiller | 600000 |  | Complete | School Condition Improvement
St.Theresa | HVAC Gym Unit | 75000 |  | Planning | School Condition Improvement | Postponed to 2025/2026 Equipment deliveries
St.Mary Haldimand | HVAC Gym unit | 75000 |  | Planning | School Condition Improvement | Postponed to 2025/2026 Equipment deliveries
St.Francis Cabrini | HVAC Gym Unit |  | 75000 | Planning | School Condition Improvement | Postponed to 2025/2026 Equipment deliveries
St.Joesph | HVAC School Ventilation PHASE 2 VRF |  | 1000000 | Complete | School Condition Improvement
Subtotal: |  | 1825000
Funding Allocation:
Unallocated/ Contingency:
SERVICES
Various Scools as required | Interior finishes Painting /millwork /Floors | 200000 |  | Complete | School Renewal Allocation
Notre Dame Brantford | Roof/HVAC | 200000 |  | Complete | School Renewal Allocation
Subtotal: |  | 400000
Funding Allocation:
Unallocated/ Contingency:
,
,

## 2023-2024
SCI- $2,489,977 - SRA - $1,828,873 Capital Funding Memo : B04 2022 |  |  | 2023-2024 CAPITAL WORKS
School | Description | Est Budget |  | Phase | Funding Source | Project Status
Site Works
St.Ceclia | Paving |  |  | Complete | School Renewal Allocation
St.Johns College | Paving |  |  | Complete | School Renewal Allocation
St.Theresa | Paving |  |  | Complete | School Renewal Allocation
St.Patrick (H) | Paving |  |  | Complete | School Renewal Allocation
Subtotal: |  | 0
Funding Allocation:
Unallocated/ Contingency:
Building Envelope
St.Gabriel | Roof replacment all sections |  |  | Complete | School Condition Improvement Allocation
Subtotal: |  | 0
Funding Allocation:
Unallocated/ Contingency:
Mechanical Works
Our Lady Of Providence | HVAC School Ventilation |  |  | Complete | School Condition Improvement Allocation
Holy Family | Boilers |  |  | Complete | School Condition Improvement Allocation
St.Patrick (B) | Boilers |  |  | Complete | School Condition Improvement Allocation
Blessed Sacrament | GYM AHU HVAC |  |  | Complete | School Condition Improvement Allocation
St.Leo | GYM AHU HVAC |  |  | Complete | School Condition Improvement Allocation
Subtotal: |  | 0
Funding Allocation:
Unallocated/ Contingency:
School Improvments
Holy Cross | Replace Interior school doors |  |  | Complete | School Renewal Allocation
Assumption College | Sports Field replacment |  |  | Complete | School Renewal Allocation
St.Johns College | Inetreior school flooring |  |  | Complete | School Renewal Allocation
Assumption College | Inetreior school flooring |  |  | Complete | School Renewal Allocation
Subtotal: |  | 0
Funding Allocation:
Unallocated/ Contingency:
,
,